## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 |  | Project Introduction & Problem Understanding | MUST HAVE | No Dependency | Shaik Ruheen Anjum | completed
S1 | S1 |  | Build Document Ingestion Pipeline (PDF, Text, APIs) | MUST HAVE | arXiv API, PubMed API | Shaik Ruheen Anjum | completed
S2 | S2 |  | PDF Parsing & Text Extraction | MUST HAVE | PyMuPDF | Shaik Ruheen Anjum | completed
S2 | S2 |  | Implement Abstractive Summarization (BART/T5/LLaMA) | MUST HAVE | Hugging Face Transformers | Shaik Ruheen Anjum | completed
S2 | S2 |  | Increase Summary Quality & Length Optimization | SHOULD HAVE | Model Tuning | Shaik Ruheen Anjum | completed
S3 | S3 |  | Domain-Specific Insight Extraction (Findings, Methods, Metrics) | MUST HAVE | Parsed Text | Shaik Ruheen Anjum | completed
S4 | S4 |  | Embedding Generation (SentenceTransformers/OpenAI) | MUST HAVE | Clean Text Data | Shaik Ruheen Anjum | completed
S5 | S5 |  | RAG Pipeline Design & Integration | MUST HAVE | Python/LangChain | Shaik Ruheen Anjum | completed
S5 | S5 |  | Vector Database Setup | MUST HAVE | Pinecone/FAISS | Shaik Ruheen Anjum | completed
S6 | S6 |  | Neo4j Database Setup | MUST HAVE | Neo4j | Shaik Ruheen Anjum | completed
S7 | S7 |  | Knowledge Graph Construction Pipeline | MUST HAVE | Graph Schema | Shaik Ruheen Anjum | completed
S8 | S8 |  | Dashboard Wireframe & UX Planning | SHOULD HAVE | Design overview | Shaik Ruheen Anjum | completed
S9 | S9 |  | Graph Query Implementation | MUST HAVE | Neo4j Setup | Shaik Ruheen Anjum | completed
S10 | S10 |  | Semantic Search Interface | MUST HAVE | RAG Pipeline | Shaik Ruheen Anjum | completed
S11 | S11 |  | Summary & Insight Display Module | MUST HAVE | Summarization Engine | Shaik Ruheen Anjum | completed
S12 | S12 |  | Project Documentation & Demo Preparation | MUST HAVE | README, PPT | Shaik Ruheen Anjum | completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7